## Sheet1
WBS ID | Task Description | Primary Owner / Role | Duration | Predecessors | Status
1 | Phase 1: Requirements & Architectural Design |  | 3 Days | - | Completed
1.1 | Stakeholder Elicitation, User Stories (US-01 to 10), SRS | Speaker 1 (PM) | 1 Day | - | Done
1.2 | Structural Modeling: Use Case & Class Diagrams | Speaker 2 (Architect) | 1 Day | 1.1 | Done
1.3 | Behavioral Modeling: Sequence & Activity Diagrams | Speaker 2 (Architect) | 1 Day | 1.2 | Done
2 | Phase 2: MERN Stack Engineering |  | 4 Days | 1 | Completed
2.1 | Express Server Setup, Schemas & JWT Auth APIs | Speaker 3 (Lead Dev) | 1 Day | 1.3 | Done
2.2 | Core REST APIs (Units, Tickets, Payments) | Speaker 3 (Lead Dev) | 1 Day | 2.1 | Done
2.3 | React Frontend Shell, AuthContext, Login/Register UI | Speaker 3 & Teammate | 1 Day | 2.2 | Done
2.4 | Tenant & Admin Interactive Dashboards + Git PR Merge | Team Collaboration | 1 Day | 2.3 | Done
3 | Phase 3: Verification & Quality Assurance |  | 1 Day | 2 | Completed
3.1 | 14-Case Testing Matrix Execution & Test_Matrix.xlsx | Speaker 4 (QA Lead) | 1 Day | 2.4 | Done
4 | Phase 4: Project Reporting & Presentation |  | 2 Days | 3 | In Progress
4.1 | GitHub README.md & Formal APA 7th Project Report | All Team Members | 1 Day | 3.1 | In Progress
4.2 | 8-Slide Deck Finalization & 10-Minute Group Defense | All Team Members | 1 Day | 4.1 | Scheduled